## RFI
REQUEST FOR INFORMATION
| To: | Dennis Alber, Contracting Officer
Federal Bureau of Investigation
Redstone Arsenal
Date:
| Solicitation #: | 15F06721R0000015 |  |  | Project Name: | New Orleans SIMUNITION HOUSE
RFI Questions
Item # | Drawing # |  | Specification # | Question |  |  | Government Response
1 |  |  | 1. SOW, Page 11 of 23, Section 4.1.7.22 | Please confirm 120V/240V, 3-Phasee, 3-wire secondary is the required voltage and phase. |  |  | 240V, 3 phase is only required for HVAC, and the Exhast fans system. No other requirement.
2 |  |  |  | Is there geotechnical reports or data available from the construction of the adjacent structure? Or soil properties from sites at the camp? |  |  | I will asked the guard again for the most recent soil compaction test at the range. There was no soil compaction test done for the building next to the construction site.
3 |  |  | SOW, Page 11 of 23, Section 4.1.12 & 4.1.7.18 | Section 4.1.7.12 states the exterior door count is 5 (all doors 3070). Section 4.1.7.18 states a sixth door size 6070. Please clarify the count and size of exterior door. |  |  | For option 2 with HVAC defensive tactics room, exterior doors are as follows: metal frame and door with dead bolt, painted white, 2 doors and one double door, approximately 36 inch and grade for commerical contruction.
4 |  |  | SOW Page 23 | For Building Option 2, is there a preference for the number of doors and door size for the 30 by 50 space? |  |  | Interior hollow core, primed, approximately 36 inch width used in typical residential new contruction.
5 |  |  | SOW, Page 11 of 23, Section 4.1.7.16 | Please clarify the number of windows for the training area, six or 8? |  |  | six windows
6 |  |  | SOW Page 23 | For Building Option 2, is there a preference for the number of exterior windows and size for the 30 by 50 space? Is there a preference for any interior window between the 70 by 50 and 30 by 50 spaces? |  |  | six windows of standard contractor grade size that would allow for a adult to climb through. We will use the windows for ventalation, and possibly to enter in some scenarios. Window should be place at a normal height in residential contruction.
7 |  |  | SOW, Page 11 of 23, 4.1.7.20 | Is there a copy of Attachment X – Door Design Drawings available? |  |  | Specs and bid from breaching door contractor in the amount of approximately $20,000 delivered will be resent to all vendors. See Attachment N.
8 |  |  | Wage Determination Sheet | LA 20200041 is for Orleans Parish. Please confirm the Orleans Parish or should we use LA202100044 for St Tammany Parish? |  |  | The solicitation will be updated to reflect LA202100044 for St Tammany Parish. See Attachment K
9 |  |  | NDA | For the Phase II proposal, is a single NDA executed by the principal for the prime contractor sufficient for the proposal phase? We could submit individual/firm NDAs for subcontractors with the award documents. |  |  | An NDA is only required by the Prime contractor for Phase II and will be required for all Subcontractors after contract award.
10 |  |  | NDA | Will the NDA project name be updated. |  |  | The solicitation will be updated with the correct NDA referencing the current solicitation. See Attachment B.
11 |  |  | SOW, Page 11 of 23, 4.1.7.6 & 4.1.7.9 | Please clarify these statements with regards to the number of interior stairs and exterior stairs. We understand the statements to require two (2) stairs (with landings), and one (1) interior stair (straight). |  |  | one mandatory stair to the mezzanine, with a second optional stair, and an optional exterior stair. Interior stair should be one with landing and one straight.
12 |  |  | Solicitation | Page 3 referenced dates for RFIs that are after the due date for the Phase II proposal. |  |  | RFI response date is changed from 12 Mar 2020 to 16 Feb 2020
13 |  |  |  | Please provide the finish floor elevation for the mezzanine from the concrete slab. |  |  | not less than 9 feet. The elevation between the finish mezzanine support structuce and the finished ground floor should be a minuim of 98 inches to allow for 8 foot walls with space to allow for contruction and deconstruction without altering any supporting structure
14 |  |  |  | Please provide the live load requirements for the stairs, mezzanine, and catwalks for design. Or should we assume 40 PSF (Stairs and Catwalks) and 80 PSF (mezzanine)? |  |  | 40PSF stairs/80 PSF mezzanine.
15 |  |  |  | Please advise if we have to include a copy of the original Bid Bond for Phase 2 or needs to be the original copy? |  |  | A copy can be submitted via email, however the original must be mailed.
16 |  |  |  | The bid schedule has 3 base bid line items. Item 0002 is for the construction of the PEMB, but the last page of the SOW lists 3 options for the PEMB. If 3 options are to be priced, item 0002 will need to somehow be broken down so that each of the 3 options can be priced. Does the Gov already have one option in mind, or does the gov want all 3 options priced? |  |  | Yes option #2 which provides for HVAC in the defensive tactical room is the preffered design. As long as this design is under the maxiumn price there is no need to provide a price on the other designs. Other designs were provided in the event that no vendor can complete the desired option 2 under the max amount.
17 |  |  |  | Are we to include all of the phase 1 proposal within our phase 2 proposal or just the references, certs, non-disclosure statements and pricing? |  |  | Yes all of Phase 1 documents should be include in Phase 2 proposal.
18 |  |  |  | Can a cutsheet for the breaching doors be provided? Q&A No. 46 says that attachment X was given along with Amendment 4, but Amendment 4 only appears to be one page. |  |  | Cut sheet?? A spec sheet and a bid from the contractor for the breaching doors was provided and can be provided again if needed.
19 |  |  |  | RFI No. 36 says that the building options on the last page of the SOW will be updated (specifically option 3 should be 50 x 80). Is this revision still forthcoming? |  |  | Option 3 should be 50 x 80. The updated SOW has been posted.
20 |  |  | RFP Section: XI. Instructions for preparing proposals | This section mentions "a separate Pricing Model 33 Divisions (Attachment L)" This attachment is not included in the documents. Please clarify. |  |  | Pricing Model 33 Divisions Attachment has been uploaded and renamed as Attachment E.
21 |  |  |  | In our Phase 1 submittal we included an original of the bid bond. Can we include a copy of this original bid bond or do we need to submit another original copy? |  |  | A copy can be submitted via email, however the original must be mailed.
22 |  |  |  | SOW reference 4.1.7.20 – reference is made to Attachment “X” – Attachment X was not supplied with the scope documents – can you distribute the Attachment “X”? |  |  | Specs and bid from breaching door contractor in the amount of approximately $20,000. See Attachment N.
23 |  |  |  | In the Phase 2 submission document, Section 3, I – a cutoff date for RFI questions is indicated as 12 March 2021 while the submission is listed for 10 March 2021 – what is the cutoff date for RFI submittals. |  |  | The cutoff date is 12 Feb 2021.
24 |  |  | Schedule of Supplies/Services | The CLIN Schedule does not include line items to list the three (3) PEMB Options. Please clarify. |  |  | CLIN has been updated to reflect option to provide option pricing.
25 |  |  | 4.1.7.6 Sniper Platform | Please clarify if the sniper platform is a stand alone structure from the PEMB or is a structure over the PEMB roof line. |  |  | The contractor can make a choice what is the most cost effective option, it can be a stand alone, a balcony, on top of the roof or an opening in teh bagle area. This is a nice to have feature but not mandatory, if you have met all of the requirements of Option 2.
26 |  |  | 4.1.7.6 Sniper Platform | State the intent of the Sniper Platform. Will the precision marksman team shoot live rounds at the targets on the range? |  |  | Yes
27 |  |  | 4.1.7.6 Sniper Platform | Where should we list the Sniper Platform’s Option for the additional deck and overhead coverage with safety harness? CLIN 0006 does not include an additional line for this Option. |  |  | No Safety harness, should have some sort of railing or knee wall. Knee wall should have an opening or space to provide space to shoot from a prone position. CLIN has been updated to allow for optional pricing.
28 |  |  | RFP Section: XI Instructions for preparing proposals | Please confirm the Government wants 1 original via Email as well as 1 CD, to be Mailed to the address stated in the SF1442? If the CD is required can it be Mailed out following the proposal due date? |  |  | Yes 1 orignal via email and a copy via CD to be mailed to the address on the SF 1442. The CD must be received within 7 calendar days.
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139