## Material Submittals Schedule
Project Number: MAHG20-1053 | [8 empty] | Project Title: B1101 DATA CENTER HVAC UPGRADES | [9 empty] | Solicitation / Contract Number: NOT AVAILABLE
Line Number | (To be completed by Project Engineer) | [13 empty] | (To be completed by Contract Administrator)
|  | Number of Copies Required (if not electronically submitted) | [20 empty] | Remarks
| Item or Description of Item, Contract Reference, Type of Submittal | Certificate of Compliance | Shop Drawings | Samples | Color Selection | Manufacturer's Recommendation | Warranty-Manufacturer and/or Workmanship | Catalog Data | Operating Instructions | Schedules, Listings, Reports, Plans | Technical Data | Test Reports | Field Reports | Required Submission Date | Date Received in Contracting | Date to Civil Engineering | Return Suspense Date | Submittal Numbers | Date Contractor Notified |  | Contractor Resubmittal | Final Approval
[19 empty] | Approved | Disapproved
1 | HazMat Questionnaire | [9 empty] | 3 | 3 | 3 | 5 Days Prior to Start Date
2 | HazMat MSDS | [9 empty] | 3 | 3 | 3 | 5 Days Prior to Start Date
3 | Hazmat Reporting Entry Form | [9 empty] | 3 | 3 | 3 | 5 Days Prior to Start Date
4 | Hazmat Reporting Entry Form | [9 empty] | 3 | 3 | 3 | End of Contract
5 | Recycling and Landfill Report | [9 empty] | 3 | 3 | 3 | End of Contract
6 | Warranty (Manufacturer's) | [11 empty] | 3 | End of Contract
7 | Warranty (Contractor's) | [11 empty] | 3 | End of Contract
8 | AF3065 Project Schedule | [9 empty] | 3 | 3 | 3 | Within 7 days of NTP, updated weekly | [8 empty] | Identify NTP, Work Start, Work End Dates, and End of Contract
9 | New CRAC units |  |  |  |  | 1 |  |  | 1 | 1 | 1 |  |  | Within 10 days of notice to proceed
10 | Existing CRAC unit 246 2way CHW CV inlet retrofit |  |  |  |  | 1 |  |  | 1 | 1 | 1 |  |  | Within 10 days of notice to proceed
11 | Existing CRAC unit 246 VFD controller & Fan Motor retrofit |  |  |  |  | 1 |  |  | 1 | 1 | 1 |  |  | Within 10 days of notice to proceed
12 | Existing CRAC unit 246 I-COM control display retrofit |  |  |  |  | 1 |  |  | 1 | 1 | 1 |  |  | Within 10 days of notice to proceed
13 | CRAC unit Factory Test Plan | [9 empty] | 1 |  |  | Within 10 days of notice to proceed
14 | CRAC unit Field "Start-Up" Test Plan | [9 empty] | 1 |  |  | Within 10 days of notice to proceed
15 | CHW, HW, CFW, and DRAIN pipe, valves & fittings |  |  |  |  | 1 |  | 1 |  | 1 | 1 |  |  | Within 10 days of notice to proceed
16 | Air Filters | [6 empty] | 1 |  | 1 | 1 |  |  | Within 10 days of notice to proceed
17 | CRAC unit Controls, Unit-Unit network switch Local Data Center COMMS |  |  |  |  | 1 |  |  | 1 | 1 | 1 |  |  | Within 10 days of notice to proceed
18 | CRAC unit Controls, BAS, EMCS BACNet MSPT COMMS |  |  |  |  | 1 |  |  | 1 | 1 | 1 |  |  | Within 10 days of notice to proceed
19 | CHW Pressure/Leak Test |  |  |  |  | 1 |  |  |  | 1 | 1 | 1 |  | 10 days following Test
20 | HFW Pressure/Leak Test |  |  |  |  | 1 |  |  |  | 1 | 1 | 1 |  | 10 days following Test
21 | CFW OP/Leak Test |  |  |  |  | 1 |  |  |  | 1 | 1 |  | 1 | 10 days following Test
22 | Drain OP/Leak Test |  |  |  |  | 1 |  |  |  | 1 | 1 |  | 1 | 10 days following Test
23 | CHW OP/Balance Test |  |  |  |  | 1 |  |  |  | 1 | 3 | 1 |  | 10 days following Test
24 | HW OP/Balance Test |  |  |  |  | 1 |  |  |  | 1 | 3 | 1 |  | 10 days following Test
25 | Electrical |  | 1 | 1 |  | 1 | 1 |  |  | 1 | 1 |  |  | Within 10 days of notice to proceed
26 | CRAC Units Factory Test Reports (4 NEW Units) | 1 | 1 |  |  | 1 | 3 | 1 | 1 | 3 | 3 | 3 |  | With delievry of CRAC units
27 | CRAC Units O & M Manual, Maintenance Data |  |  |  |  | 1 |  |  | 1 | 3 | 3 |  |  | End of Contract
28 | CRAC Units Manufacturer Start-Up Test Reports (4 Units) | 1 |  |  |  | 1 | 3 |  |  | 3 | 3 | 3 |  | End of Contract
29 | CRAC Unit Manufacturer Start-Up Test Reports (1 RETROFIT Unit) | 1 |  |  |  | 1 | 3 |  |  | 3 | 3 | 3 |  | End of Contract
30 | EMCS control monitoring & alarm points list confirmation report (5 Units) | 1 |  |  |  | 1 | 3 |  |  | 3 | 3 | 3 |  | End of Contract
Note on P5: Enter the due date from the Contractor (MM/DD/YY)
Note on Q5: Enter the date received from the Contractor. (MM/DD/YY)
Note on R5: Enter the date submittal was given to CE for review. (MM/DD/YY)
Note on S5: Enter the date the submittal is due back from CE (MM/DD/YY)
Note on T5: Enter the Submittal Number
Note on U6: Enter date the Contractor was notified of submittal approval (MM/DD/YY)
Note on V6: Enter date the Contractor was notified of submittal disapproval (MM/DD/YY)
Note on W5: Enter Resubmittal Number
Note on X5: Enter the submittal final approval date (MM/DD/YY)